## Project schedule
| Gantt Chart – Project Timeline for Web-Based IT Supervisor Portfolio | [5 empty] | Project start: | [7 empty] | 2025-05-26
[7 empty] | Display week: | [7 empty] | 1
[7 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-22 | [6 empty] | 2025-06-29 | [6 empty] | 2025-07-06 | [6 empty] | 2025-07-13
| TASK | PROGRESS | START | END | Duration (Days) | time axis 2025-05-26 to 2025-07-19
 | time axis 2025-05-26 to 2025-07-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Milestone 1 – Coaching & Communication Toolkit Completion
| Define Communication Objectives | 100% | 2025-05-26 | 2025-05-30 | 5 | 5
| Create Communication Templates | 100% | 2025-05-31 | 2025-06-04 | 5 | 5
| Develop Coaching Toolkit Resources | 100% | 2025-06-05 | 2025-06-12 | 8 | 8
| Gather Feedback and Iterate | 100% | 2025-06-13 | 2025-06-18 | 6
| Publish Coaching & Communication Section | 100% | 2025-06-19 | 2025-06-25 | 7 | 7
Milestone 2 – KPI Dashboard & Financial Tools Development
| Identify Key Performance Indicators | 100% | 2025-06-26 | 2025-06-26 | 1 | 1
| Design Budget Planning Layout | 100% | 2025-06-27 | 2025-06-28 | 2 | 2
| Develop Interactive KPI Dashboard | 100% | 2025-06-29 | 2025-06-30 | 2 | 2
| Integrate Resource Allocation Tools | 100% | 2025-07-01 | 2025-07-03 | 3
| Team Leadership & HR Template Creation | 100% | 2025-07-04 | 2025-07-05 | 2
| Publish KPI and Leadership Sections | 100% | 2025-07-06 | 2025-07-07 | 2 | 2
Milestone 3 – Ethics Section & Full Site Deployment
| Develop Ethics & Inclusion Framework | 0% | 2025-07-08 | 2025-07-12 | 5 | 5
| Design Cultural Adaptation Materials | 0% | 2025-07-13 | 2025-07-16 | 4 | 4
| Finalize Website UI & Design Elements | 0% | 2025-07-17 | 2025-07-21 | 5 | 5
| Integrate All Portfolio Sections | 0% | 2025-07-22 | 2025-07-27 | 6 | 6
| Record Final Video & Publish Website | 0% | 2025-07-28 | 2025-07-30 | 3 | 3
APA Citation
Sankaranarayanan, S. (2023). Strategies Automotive Manufacturing Managers Use to Deliver Work in Alignment with Project Milestones (Doctoral dissertation, Walden University). https://search.proquest.com/openview/1ae9af70f1cbc6b4f406c386a5ad9349/1?pq-origsite=gscholar&cbl=18750&diss=y
Vasankari, P. (2024). The Effect of Project Communication and Project Performance: The Role of Detailed Gantt Chart in Substation Construction Project. https://www.theseus.fi/handle/10024/850369
Note. Adapted from Sankaranarayanan (2023) and Vasankari (2024).